## Sheet1
Document | Information Baseline | Created in: | Accountable | Responsible
Benefits Profiles | Boundary | Identifying a Programme | Senior Responsible Owner | Business Change Manager
Benefits Maps | Programme | Defining a Programme | Senior Responsible Owner | Business Change Manager
Benefits Management Strategy | Governance | Defining a Programme | Senior Responsible Owner | Programme Manager
Benefits Realisation Plan | Tool | Defining a Programme | Senior Responsible Owner | Programme Manager
Blueprint | Boundary | Defining a Programme | Senior Responsible Owner | Programme Manager
Business Case | Programme | Identifying a Programme | Senior Responsible Owner | Programme Manager
Information Management Strategy | Governance | Defining a Programme | Programme Manager | Programme Manager
Information Management Plan | Tool | Defining a Programme | Senior Responsible Owner | Programme Manager
Isue Log | Tool | Identifying a Programme | Senior Responsible Owner | Programme Manager
Issue Resolution Strategy | Governance | Defining a Programme | Senior Responsible Owner | Programme Manager
Monitor and Control Strategy | Governance | Defining a Programme | Senior Responsible Owner | Programme Manager
Organization Structure | Governance | Defining a Programme | Senior Responsible Owner | Programme Manager
Programme Brief | Boundary | Identifying a Programme | Sponsoring Group | Senior Responsible Owner
Programme Communications Plan | Tool | Defining a Programme | Programme Manager | Programme Manager
Programme Definition Document | Programme | Defining a Programme | Sponsoring Group | Programme Manager
Programme Mandate | Boundary | Outside of Programme | Sponsoring Group | Senior Responsible Owner
Programme Plan | Tool | Defining a Programme | Senior Responsible Owner | Programme Manager
Programme Preparation Plan | Tool | Identifying a Programme | Senior Responsible Owner | Programme Manager
Project Dossier | Programme | Defining a Programme | Senior Responsible Owner | Programme Manager
Quality Management Strategy | Governance | Defining a Programme | Senior Responsible Owner | Programme Manager
Quality Management Plan | Tool | Defining a Programme | Programme Manager | Programme Manager
Resource Management Strategy | Governance | Defining a Programme | Senior Responsible Owner | Programme Manager
Resource Management Plan | Tool | Defining a Programme | Programme Manager | Programme Manager
Risk Management Strategy | Governance | Defining a Programme | Senior Responsible Owner | Programme Manager
Risk Register | Tool | Identifying a Programme | Senior Responsible Owner | Programme Manager
Stakeholder Profles | Tool | Defining a Programme | Business Change Manager | Programme Manager
Stakeholder Engagement Strategy | Governance | Defining a Programme | Senior Responsible Owner | Programme Manager
Vision Statement | Boundary | Identifying a Programme | Sponsoring Group | Senior Responsible Owner